## Sheet1
Sl no | Deliverable/Day | D-01 | D-02 | D-03 | D-04 | D-05 | D-06 | D-07 | D-08 | D-09 | D-10 | D-11 | D-12 | D-13 | D-14 | D-15 | D-16 | D-17 | D-18 | D-19 | D-20 | D-21 | D-22 | D-23 | D-24 | D-25 | D-26 | D-27 | D-28
1 | Selection Project Topic | bar: D-01 to D-02
2 | Preliminary Research Work | bar: D-02 to D-06
3 | Literature Review | bar: D-02 to D-06
4 | Research on Methodology | bar: D-02 to D-06
5 | Submission of Extended Proposal | bar: D-06
6 | Proposal Defense | bar: D-10
7 | Project Development Work Continues | bar: D-07 to D-09
8 | Submission of Interim Draft Report | bar: D-10
9 | Submission of Interim Report | bar: D-11
10 | Project Development Work Continues | bar: D-12 to D-17
11 | Submission of Progress Report | bar: D-18
12 | Project Development Work Continues | bar: D-19 to D-24
13 | Pre-SEDEX | bar: D-25
14 | Submission of Draft Report | bar: D-25
15 | Sumission of Dissertation (soft bound) | bar: D-25
16 | Oral Presentation | bar: D-26
17 | Documentation work continues | bar: D-27
18 | Submission of Technical paper | bar: D-28
19 | Sumission of final Dissertation | bar: D-28