## Sheet1
Sl no: | Activitys: | Start Date: | End Date: | Duration: | 2016-07-01 | 2017-07-01 | 2018-07-01 | 2019-07-01 | 2020-07-01 | 2022-07-01 | 2023-07-01 | 2024-07-01 | 2025-07-01 | 2026-07-01 | 2027-07-01 | 2029-07-01 | 1930-07-01 | 1931-07-01 | 2001-08-01 | 2002-08-01 | 2003-08-01 | 2005-08-01 | 2006-08-01 | 2007-08-01 | 2008-08-01 | 2009-08-01 | 2010-08-01 | 2012-08-01 | 2013-08-01 | 2014-08-01
[5 empty] | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed
1 | Language Translation Application Using Python | 2024-07-16 | 2024-08-14 | 22 Days
2 | Project Planning and Setup | Jul 16, 2024 | Jul 19, 2024 | 4 days | Tue: Project Planning
3 | Research Plan | Jul 16, 2024 | Jul 16, 2024 | 1 day | Tue: Research Plan
4 | Setup Environment | Jul 17, 2024 | Jul 17, 2024 | 1 day | Wed: Set Up
5 | Loading Dataset | Jul 18, 2024 | Jul 18, 2024 | 1 day | Thu: Loading Data
6 | Preprocess to Translate | Jul 19, 2024 | Jul 19, 2024 | 1 day | Fri: Process to Translate; Sat: to Translate
7 | AI Analysis | Jul 22, 2024 | Jul 26, 2024 | 5 days | Mon: AI Analysis
8 | Select and Implement Algorithm | Jul 22, 2024 | Jul 24, 2024 | 3 days | Mon: Select and Impliment
9 | Testing With Googletrans | Jul 25, 2024 | Jul 26, 2024 | 2 days | Thu: Testing With Googletrans
10 | User Input | Jul 29, 2024 | Jul 29, 2024 | 1 day | Mon: User Input
11 | Display Results | Jul 30, 2024 | Jul 31, 2024 | 2 days | Mon: Display Results
12 | Evaluation and Optimization | Aug 01, 2024 | Aug 07, 2024 | 5 days | Thu: Evaluation and Optimization
13 | Evaluate Algorithm | Aug 01, 2024 | Aug 02, 2024 | 2 days | Thu: Evaluate Algorithm
14 | Analyze Results | Aug 05, 2024 | Aug 05, 2024 | 1 day | Mon: Analyze Results
15 | Implimented Google Translate API | Aug 06, 2024 | Aug 07, 2024 | 2 days | Tue: Implimented Google Translate API
16 | Explore Alternatives | Aug 08, 2024 | Aug 08, 2024 | 1 day | Thu: Explore Alternatives
17 | Deployment and Finalization | Aug 09, 2024 | Aug 14, 2024 | 4 days | Fri: Deployment and Finalization
18 | Develop User Interface | Aug 09, 2024 | Aug 12, 2024 | 2 days | Fri: Develop User Interface
19 | User Testing | Aug 13, 2024 | Aug 12, 2024 | 1 day | Tue: User Testing
20 | Documentation | Aug 14, 2024 | Aug 14, 2024 | 1 day | Wed: Documentation
21 | Final Review | Aug 14, 2024 | Aug 14, 2024 | 1 day | Wed: Final Review
22 | Project Presentation | Aug 14, 2024 | Aug 14, 2024 | 1 day | Wed: Project Presentation